## Sheet1
Name
Project
Phase | Activities | Task | Subtask | Number | Per Task | Estimate | Actual | Units | Amount Assigned | Effciency | Duration
Product Definition
| Featuere Diagram |  |  | 10
|  | Familirizing inkscape |  |  |  | 4 | 6 | Hours
|  | Preparing version one |  |  |  | 2 | 4 | Hours
|  | Revisualizing the whole project |  |  |  | 3 | 2 | Days
|  | Feature diagram vesion 2 |  |  |  | 5 | 3.5 | Hours
|  | Revisng and recorrection |  |  |  | 4 | 2.5 | Hours
| Feature List | Refering to similar format |  |  |  | 3 | 4 | Hours
Behavior Description
Interface List
|  | Preparing version 1 on Notepad++ |  |  |  | 1 | 1 | Days
Architecture |  | Revising and correcing |  |  |  | 2 | 2 | Hours
Majot Components BOM
|  | Datasheet study |  |  |  | 4 | 6 | Hours
|  | Preparing Characterstics comparison |  |  |  | 2 | 2 | Hours
|  | Preparing BOM Spreadsheet |  |  |  | 2 | 2 | Hours
Complete BOM
|  | Datasheet study |  |  |  | 1 | 2 | Hours
|  | Preparing BOM Spreadsheet |  |  |  | 2 | 3 | Hours
| Hardware Block diagram | Intial diagram preparation |  |  |  | 6 | 8 | Hours
|  | Revisting and correcting |  |  |  | 1.5 | 1.5 | Hours
Product Architecture
Major Signals Characteristics
Current Budget
Pinouts
Calculations
Realization
Detailed Design
Bypassing
Damage Protection
ESD and EMI Protection
Design for Test
Board Design
|  | Library |  | 10 | 0.5 | 5 |  | 50% | 100% | 50% | 20
Schematic
|  |  | Local Wiring | 10 | 0.25 | 2.5
|  |  | Global Wiring |  |  | 2
Layout
BOM
Cable Design
Manufacturing Package
Manufacture
Procurement
Kitting
Fabrication
Assembly
Enclosure Assembly
Cable Assembly
System Assembly
Bring Up
Set Up
Base Line Existing Hardware
Board Induction
Smoke Test
Debug Cycle
Test
Test Setup
Testing the Test
Testing
Analysis Development
Analysis
[5 empty] | Project Hours | 52
| Project Management |  |  |  |  | 5.2
57.2
| Contingency Time |  |  |  |  | 15.6
72.8