## Sheet1
Name
Project
Phase | Task | Sub Task | Number | Per Task | Estimate | Actual | Units | Amount Assigned | Effciency | Duration
Product Definition
Featuere Diagram
|  | Familirizing inkscape |  |  | 4 | 6 | Hours
|  | Preparing version one |  |  | 2 | 4 | Hours
|  | Revisualizing the whole project |  |  | 3 | 2 | Days
|  | Feature diagram vesion 2 |  |  | 5 | 3.5 | Hours
|  | Revisng and recorrection |  |  | 4 | 2.5 | Hours
| Product Definition | Refering to similar format |  |  | 3 | 4 | Hours
|  | Preparing version 1 on Notepad++ |  |  | 1 | 1 | Days
Architecture |  | Revising and correcing |  |  | 2 | 2 | Hours
Majot Components BOM
|  | Datasheet study |  |  | 4 | 6 | Hours
|  | Preparing Characterstics comparison |  |  | 2 | 2 | Hours
|  | Preparing BOM Spreadsheet |  |  | 2 | 2 | Hours
Complete BOM
|  | Datasheet study |  |  | 1 | 2 | Hours
|  | Preparing BOM Spreadsheet |  |  | 2 | 3 | Hours
| Hardware Block diagram | Intial diagram preparation |  |  | 6 | 8 | Hours
|  | Revisting and correcting |  |  | 1.5 | 1.5 | Hours
Realization
Bring Up
Test